## Owner-Date Analysis
Item | Task / Milestone | Earlier Owner / Date | Later Owner / Date | Meetings | Nature | Verified
1 | Compliance sign-off on masking rules and security implementation | Priya (Compliance) / 18 Aug 2026 | Priya (Compliance) / 27 Aug 2026 | M02, M05, M07 | Formally documented deadline change | Yes
2 | Duplicate customer ID corrections in legacy migration data | Neha / Data Team (overall migration ownership) | Data Governance Team (duplicate-ID correction; Neha coordinated) | M01, M06, M08 | Formally documented ownership clarification | Yes
3 | Session-timeout warning text fix | Meera (Frontend) / due 1 Sep 2026 | Meera (Frontend) / completed 7 Sep 2026 | M07, M10 | Execution tracking / completed after planned deadline | Yes
4 | Production SSO certificate escalation and receipt | Request submitted 19 Aug 2026; contingency threshold 18 Sep 2026 | Certificates received 14 Sep 2026; connectivity passed 15 Sep 2026 | M04, M11, M12, M13 | Risk resolution before contingency threshold | Yes
5 | Post-launch metrics and final pilot quality report | No earlier deadline; structure established in M15 | Rahul, Meera & Neha: metrics by 3 Oct 2026; Karan: report by 5 Oct 2026 | M15 | Formally documented staggered task structure | Yes
Overall Finding | No genuine owner/date errors or unresolvable conflicts were identified. |  |  |  |  | Verified

## Summary
Finding | Result
Genuine owner/date conflicts | None identified
Documented changes / clarifications reviewed | 5
Source | All 15 NovaCRM meeting transcripts
Verification | Completed